## Sheet1
Tasks	Validation	Assignee	Deadline	5	6	7	8	9	10	11	12	13	14	15	16	17
				13 Feb	20 Feb	27 Feb	5 Mar	12 Mar	19 Mar	26 Mar	2 Apr	9 Apr	16 Apr	23 Apr	30 Apr	7 May
Communication Primitives
I2C Communication	Milestone 1	Via, Justin	–
GPSr UART communication	Using a bus sniffer, verify that NMEA data is travelling over the UART. Then using a bus master device, request position data over I2C	Via	1 March
PIC to MiWi communication	Successful read & write to MiWi registers (e.g. set Tx power, then read to verify setting)	Via	1 March
Long Distance I2C Communication	Successful reliable communications along 75'+ of cabling	Mitch	6 March
MiWi <> MiWi communication	Sending predetermined bytestrings over MiWi with confirmed reception	Via, Mitch	16 March

PIC Software
Adapt existing 2680 code to 45J10	Using a bus sniffer, verify I2C read/write operations are successful to all 45J10 devices	Via	28 February

Arm Board Software
Test Position Data to Web Server	Changing position data is able to be displayed on the webpage (even if the 'changing' data is just hardcoded at this time)	Andrew, Justin	9 March
GPS Data to ARM board	GPS position is displayed on ARM	Via, Justin	20 March
Filesystem	Successful text file creation on a computer-readable filesystem	Via	13 March
Fancy Display	The fancy display looks nice, and has spots for pertinent information to go	Andrew	13 March
Web Server	Custom content is displayed on the webpage	Andrew	1 March
Position Calculation on ARM	Position calculator output is fed to ARM display and other interfaces	Mitch, Justin	18 March

Integration
Actual Position Data to Web Server	GPSr position data, and calculated position is displayed on the webpage	ALL the people	5 April
Position Data to Filesystem	GPSr position data, and calculated position is written to a flat text file	ALL the people	5 April
Position Data to Display	GPSr position data, and calculated position is displayed on the 'fancy display'	ALL the people	5 April
Final Project Demonstration	Project completed, demonstrated	ALL the people	24 April
Final Report	Report completed, submitted.	ALL the people	3 May
Board Assembly	It works	ALL the people	20 March

Design Dependencies
Position Calculation Algorithm	Given reasonable RSSI input, the position calculator provides some reasonable position output	Mitch	9 March
Node PCB design	It exists	Mitch, Andrew	9 March
Calibration Sequence	ARM Display or Web page displays GPS position of all three receiever nodes	Andrew	27 March

To Node PCB

From Long Distance I2C

From GPS Data to ARM

To Arm board
GPSr communication